## Sheet1
COMMUNITY ENGAGEMENT PROJECT (CEP) - LOGBOOK
Project Title: Greenergy: A Data Driven tree plantation calculator for pollution control.
Project Guide: Prof. Archana Kadam
PRN No | Name of Student
124B1B334 | Varun Shrotri
124B1B337 | Palash Kurkute
125B2B027 | Jayesh Harihar
Date | Work Done / Description | Module / Feature | Remarks
07 Jan (Wed) | Discussed 'Greenergy' concept | Project Initiation
09 Jan (Fri) | Finalized Tech Stack: React 18, Vite, and TailwindCSS for the frontend. | Planning & Setup
14 Jan (Wed) | Minor Blocker: Evaluated Redux vs. Context API for global state. Decided on Redux Toolkit. | State Management
16 Jan (Fri) | Requirement analysis: Identified core features like AQI metrics and Heatmaps. | Requirements Analysis
21 Jan (Wed) | Wireframing initial UI on Figma; planned responsive dashboard layout. | UI/UX Design
23 Jan (Fri) | Setup project directory structure, installed dependencies, and configured Tailwind. | Project Foundation
28 Jan (Wed) | Implemented global styling, typography, and primary color palette. | Design System
30 Jan (Fri) | Created reusable Layout components (Sidebar, Navbar) using Framer Motion. | UI Components
04 Feb (Wed) | Built the Landing Page with mission statement and project overview. | Frontend Dev
06 Feb (Fri) | Set up React Router v6 for navigation between Dashboard and Heatmap pages. | Routing
11 Feb (Wed) | Delay: Researched D3.js vs. Recharts for the heatmap implementation. | Research
13 Feb (Fri) | Discussion with team regarding API structure for fetching real-time weather data. | Database/API Planning
18 Feb (Wed) | Started development of the Main Dashboard; implemented card-based metric displays. | Dashboard Module
20 Feb (Fri) | Integrated Recharts to show historical AQI trends for selected cities. | Data Visualization
25 Feb (Wed) | Blocker: Faced issues with data fetching during API integration. Debugging async calls. | API Integration
27 Feb (Fri) | Successfully fetched live AQI data; implemented error handling for empty states. | Backend Connectivity
04 Mar (Wed) | Developed the dynamic AQI Heatmap using D3.js; integrated color-coded zones. | Heatmap Module
06 Mar (Fri) | Added pollutant selection feature (PM2.5, NO2, O3) to the heatmap filters. | Advanced Filtering
11 Mar (Wed) | Human Factor: Day spent cleaning up redundant CSS and optimizing asset loading. | Refactoring
13 Mar (Fri) | Integrated health advisory logic based on WHO pollutant standards. | Health Advisory
18 Mar (Wed) | Designed and implemented User Search for specific geographic coordinates. | Search & Map
20 Mar (Fri) | Conducted cross-browser testing and fixed responsive layout break-points. | Testing & QA
25 Mar (Wed) | Ongoing: Debugged the ErrorBoundary.jsx to handle API timeout crashes. | Error Handling
27 Mar (Fri) | Refining UI transitions and adding tooltips for complex data points. | UI/UX Improvement